## Sheet1
Id | Activity | Owner(s) | Completed | Comments
1 | New community request submitted | Project Owners | Done
2 | New community request review | OSS Governance, BU Leader |  | Contributing Steps to start contributing
3 | New community business case | Project Owners, OSS Governance | Done | Maintain your own contracts
4 | New community business case review | OSS Governance, BU Leader, IP Counsel, TRGR | Done
5 | Patentable material review | IP Counsel | Done
6 | Community contributor agreement | IP Counsel, OSS Governance | At to GitRepo
7 | Outbound licensing reviewed | IP Counsel, OSS Governance | Done
8 | Confirm appropriate TR copyright notices in code and documentation | OSS Governance | Done
9 | 3rd party incorporated code and dependencies license review: compatibility & attributions validation | OSS Governance | Done
10 | BU management approval | BU Leader | Done
11 | Legal IP approval | IP Counsel | Done
12 | TRGR approval | TRGR | Done
13 | OSS governance approval | OSS Governance | Done
14 | Primary maintainers assigned and time allocated | Project Owners | Done
15 | Develop promotion plan | Project Owners | Start small | CIBC Innovation, Scotia, National Bank, TD
16 | Source code review | Project Owners | Done
17 | Prebuilt binaries, install scripts, man pages | Project Owners | Done
18 | Licenses, Copyright, ReadMe, other notices | Project Owners | Done
19 | Protex scan analysis | Project Owners, OSS Governance | Send..
20 | Code Repository | Project Owners | Done
21 | Wiki / Documentation / FAQ | OSS Governance
22 | Mailing List and IRC | Project Owners | Slack
23 | Bug reporting / tracking system | Project Owners | Github
24 | URL and/or Web Site Domain | Project Owners | Done
25 | Outreach to related / dependent projects | Project Owners | In Process
27 | Execute PR and other promotion | Project Owners | Quantify it